| PIONEER VALLEY REGIONAL BROWNFIELDS CLEANUP REVOLVING LOAN FUND MAJOR TASKS CHECKLIST |  |  |  |  |
| --- | --- | --- | --- | --- |
| TASK | PVPC | BORROWER / SUBGRANTEE | STATE / PVPC’s LSP | EPA |
| General Requirements [est. 4-6 weeks; more if Historic Preservation mitigation is required] |  |  |  |  |
| Seeks approval from EPA that site and borrower/subgrantee are eligible for EPA funds |  |  |  |  |
| EPA reviews site and borrower/subgrantee for eligibility |  |  |  |  |
| Assist EPA in complying with Historic Preservation Act S.106 review for site cleanup |  |  |  |  |
| Site must be enrolled in the appropriate State response program to be eligible to receive federal brownfields cleanup funds (generally MGL Ch. 21E) |  |  |  |  |
| Designates an environmental project manager (generally a Licensed Site Professional, or LSP) to independently review the proposed cleanup plans and actions • Cannot be the borrower’s environmental contractor |  |  |  |  |
| Plan for Community Involvement [est. 1-2 weeks] |  |  |  |  |
| Designates Community Relations Spokesperson • Spokesperson must be an employee of the lead agency |  |  |  |  |
| Prepares a draft Community Relations Plan (CRP) and submits to EPA for review • CRP must be prepared before the Analysis of Brownfields Cleanup Alternatives (ABCA) is made available for public review and comment. • CRP outlines steps to provide reasonable notice of proposed cleanup, opportunity for involvement, response to comments, and administrative records that are available to the public. • CRP may be prepared by either Lead Agency or Borrower/Subgrantee. • Lead Agency is responsible for ensuring CRP compliance. |  |  |  |  |
| Reviews and comments on draft CRP |  |  |  |  |
| Establishes information repository and maintains administrative record for the site • The repository must be established before the Analysis of Brownfields Cleanup Alternatives is made available for public review and comment. |  |  |  |  |
| Analysis of Brownfields Cleanup Alternatives (ABCA) [est. 2-5 weeks; less if MCP Phase III has been prepared] |  |  |  |  |
| Drafts a remedial planning document that includes an analysis of cleanup alternatives(ABCA) • Identifies the objectives of the environmental response action and provides an analysis of cleanup alternatives. • Documents that the situation meets the need for an environmental response action. • Provides information pertaining to site background; threats to public health and/or the environment posed by the site; enforcement activities; and projected costs. • Identifies the proposed action, and explains the rational for its selection. • ABCA may be included in remedial design documents (RAP). |  |  |  |  |
| Conduct Community Involvement [est. 4-6 weeks; may be concurrent with some other steps] |  |  |  |  |
| Provides public notice of availability of draft ABCA document and conducts a 30-day public comment period |  |  |  |  |
| Conducts a public meeting during the 30-day public comment period to inform public of the proposed cleanup plans and to solicit comments |  |  |  |  |
| Reviews & comments on the draft ABCA document |  |  |  |  |
| TASK | PVPC | BORROWER / SUBGRANTEE | STATE / PVPC’s LSP | EPA |
| Decision Document [est. 1 week] |  |  |  |  |
| Prepares Decision Document identifying the selected cleanup alternative for the site • Includes response to all relevant comments during the public comment period • Documents any changes to the final cleanup plan • Can be included in final remedial action plan • Usually in the form of a memo |  |  |  |  |
| Cleanup Plan [est. 1-3 weeks; may be concurrent with ABCA] |  |  |  |  |
| Develops and submits State-required remedial design and engineering documents (i.e., RAM, RAP, HASP, etc.) to PVPC’s LSP for review • This step may occur simultaneously with the submittal of the ABCA document |  |  |  |  |
| Reviews State-required remedial design and engineering documents and provides written comment per State regulations |  |  |  |  |
| Submits copy of written comments to EPA |  |  |  |  |
| Submits budget of proposed cleanup to EPA that details activities to be funded with EPA funds |  |  |  |  |
| Reviews and approves budget of proposed cleanup activities |  |  |  |  |
| Quality Assurance Project Plan (QAPP) [est. 2-4 weeks; less if a generic QAPP is already approved by EPA] |  |  |  |  |
| Prepares site-specific quality assurance project plan if environmental sampling is to be conducted and submits to EPA for approval |  |  |  |  |
| Reviews and approves quality assurance project plan |  |  |  |  |
| Loan/Subgrant Agreement [est. 3-5 weeks] |  |  |  |  |
| Completes BCRLF application package |  |  |  |  |
| Negotiates loan/subgrant terms in consultation with PV Brownfields Advisory Committee’s Loan Review Subcommittee |  |  |  |  |
| Develops draft loan/subgrant agreement and submits to EPA for review |  |  |  |  |
| Reviews loan/subgrant agreement for inclusion of federal environmental and other cross-cutting requirements (such as Davis-Bacon, Historic Preservation, etc…) |  |  |  |  |
| Cleanup Activities [schedule is site-specific] |  |  |  |  |
| Conducts periodic site visits during implementation • Ensures compliance with approved cleanup plans • Ensures compliance with Davis-Bacon requirements (payrolls, labor interviews, signage, etc.) and state prevailing wage requirements, where applicable |  |  |  |  |
| Prepares cleanup closeout documentation at the conclusion of the cleanup and submits to PVPC’s LSP/State for review • Demonstrates that cleanup is complete and is protective of human health and the environment • Identifies any Activity and Use Limitations (AULs) utilized and long-term monitoring requirements |  |  |  |  |
| Reviews and provides written comments or approval of the cleanup closeout documentation (generally a Response Action Outcome, or RAO) |  |  |  |  |
| Submits copy of closeout documentation to EPA |  |  |  |  |